## Backend Task Plan
LDC Case Management Dashboard — Backend Data Task Plan
Source: Athena cross-account read from data team's Iceberg tables ¦ Cache: Redis (Reporting AWS account) ¦ Tiers: Snapshot (EOD/EOM) and Near-Real-Time (≤1hr) ¦ Rows flagged ⚠ need refresh-cadence confirmation (<15 min candidate)
ID | Level | Parent ID | Summary | Description | Dashboard Component | Refresh Tier | Source / Iceberg Table | Redis Cache Key (placeholder) | Cache TTL | Dependencies | Acceptance Criteria | Jira Issue Type | Priority | Status | Notes / Open Items
E1 | Epic |  | Cross-Account Athena/Iceberg Source Integration | Establish read access from Reporting AWS account to source data team's Iceberg tables via Athena/Glue/Lake Formation. | All | Infra / N-A | TBD — pending data team |  |  |  | Reporting account can successfully run a test Athena query against each required Iceberg table. | Epic | High | Not Started
E1-S1 | Story | E1 | Define cross-account IAM role & Lake Formation grant | Coordinate with source data team on trust policy and table-level grants. | All | Infra / N-A | TBD — pending data team |  |  |  | Cross-account role assumable from Reporting account; SELECT granted on required tables. | Story | High | Not Started | Blocking dependency for all downstream dbt work.
E1-S1-T1 | Sub-task | E1-S1 | Request IAM trust policy / assume-role setup from source team |  | All | Infra / N-A | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started
E1-S1-T2 | Sub-task | E1-S1 | Request Lake Formation SELECT grants on required Iceberg tables/database |  | All | Infra / N-A | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started
E1-S1-T3 | Sub-task | E1-S1 | Validate access via test Athena query against source Iceberg tables |  | All | Infra / N-A | TBD — pending data team |  |  | E1-S1-T1, E1-S1-T2 |  | Sub-task | High | Not Started
E1-S2 | Story | E1 | Document source Iceberg tables & schema mapping | Identify exact tables/columns in the source account that back each of the 20 dashboard attributes. | All | Infra / N-A | TBD — pending data team |  |  |  | Every attribute on the Attribute Refresh Mapping tab has a confirmed source table/column. | Story | High | Not Started | See 'Attribute Refresh Mapping' tab.
E1-S2-T1 | Sub-task | E1-S2 | Obtain Iceberg database/table names for LDC case request data | PLACEHOLDER — names not yet provided by source data team. | All | Infra / N-A | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started | ⚠ Placeholder
E1-S2-T2 | Sub-task | E1-S2 | Map all 20 dashboard attributes to source Iceberg column names |  | All | Infra / N-A | TBD — pending data team |  |  | E1-S2-T1 |  | Sub-task | Medium | Not Started
E1-S2-T3 | Sub-task | E1-S2 | Confirm Iceberg partitioning to support efficient hourly polling |  | All | Infra / N-A | TBD — pending data team |  |  | E1-S2-T1 |  | Sub-task | Medium | Not Started
E1-S3 | Story | E1 | Define dbt source declarations for cross-account Athena/Iceberg tables | Wire the confirmed tables into dbt as sources with freshness checks. | All | Infra / N-A | TBD — pending data team |  |  | E1-S2 | dbt source freshness check passes and is aligned to the assigned refresh tier. | Story | Medium | Not Started
E1-S3-T1 | Sub-task | E1-S3 | Add Athena source block to dbt sources.yml for source team's Glue database |  | All | Infra / N-A | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E1-S3-T2 | Sub-task | E1-S3 | Add dbt source freshness checks aligned to refresh tier SLA |  | All | Infra / N-A | TBD — pending data team |  |  |  |  | Sub-task | Low | Not Started
E2 | Epic |  | dbt Staging Layer | Clean/cast raw Iceberg fields into typed staging models; no aggregation. | All | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E1 | Staging models build cleanly and pass schema tests. | Epic | High | Not Started
E2-S1 | Story | E2 | Build stg_ldc_case_requests | One row per request with typed/cleaned fields. | Case Queue, Status Summary, Filters | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E1-S2 | Model documented and tested; status/sub-status enums validated. | Story | High | Not Started
E2-S1-T1 | Sub-task | E2-S1 | Cast/clean raw fields (dates, IDs, status enums) into typed staging model |  | Case Queue | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started
E2-S1-T2 | Sub-task | E2-S1 | Standardize Submitter Group / Reviewer Group enum values | Submitter Group: External Submitter, LDC, MSOPE, CURE, DVC, IR. Reviewer Group: Auto-Decision, LDC, Sec Policy. | Case Queue, Filters | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E2-S1-T3 | Sub-task | E2-S1 | Add schema.yml not_null/accepted_values tests on status & sub status |  | Case Queue | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E2-S2 | Story | E2 | Build stg_ldc_loan_attributes | Loan-level records supporting Loan Count / Attribute Count aggregation. | Case Queue | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E1-S2 | Model documented and tested; supports per-request rollups. | Story | Medium | Not Started
E2-S2-T1 | Sub-task | E2-S2 | Stage loan-level attribute records for Loan Count / Attribute Count rollups |  | Case Queue | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E2-S2-T2 | Sub-task | E2-S2 | Add not_null/unique tests on loan-level keys |  | Case Queue | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Low | Not Started
E3 | Epic |  | dbt Mart Layer | Pre-aggregated mart tables, one per dashboard component. | All | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E2 | All marts built, tested, documented in schema.yml. | Epic | High | Not Started
E3-S1 | Story | E3 | Build mart_ldc_case_queue | One row per Request No. covering all 16 Case Management Queue table columns. | Case Queue Table | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E2-S1, E2-S2 | Mart returns correct row for each of the 17 sample requests in prototype; all columns populated. | Story | High | Not Started
E3-S1-T1 | Sub-task | E3-S1 | Aggregate to one row per Request No. covering all 16 queue table columns |  | Case Queue Table | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started
E3-S1-T2 | Sub-task | E3-S1 | Implement Queue Age calculation | PLACEHOLDER — business rule for elapsed time (calendar vs. business hours) TBD. | Case Queue Table | ⚠ TBD (<15min?) | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started | ⚠ Needs business rule clarification
E3-S1-T3 | Sub-task | E3-S1 | Implement Cycle Time calculation | PLACEHOLDER — business-day vs. calendar-day rule, and behavior pre-completion, TBD. | Case Queue Table | ⚠ TBD (<15min?) | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started | ⚠ Needs business rule clarification
E3-S1-T4 | Sub-task | E3-S1 | Implement SLA Status derivation logic | PLACEHOLDER — thresholds for Within SLA / At Risk / Breached not yet defined. | Case Queue Table, Filters | ⚠ TBD (<15min?) | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started | ⚠ Needs business rule clarification
E3-S1-T5 | Sub-task | E3-S1 | Document columns + dbt tests in schema.yml |  | Case Queue Table | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E3-S2 | Story | E3 | Build mart_ldc_status_summary | Counts per Request Status for the clickable summary bar chart. | Status Summary Chart | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E2-S1 | Chart counts match Draft/Exception Review/Pending Reclass/Completed/Canceled/Rejected totals from prototype. | Story | High | Not Started
E3-S2-T1 | Sub-task | E3-S2 | Aggregate counts per Request Status for summary chart | Draft, Exception Review, Pending Reclass, Completed, Canceled, Rejected. | Status Summary Chart | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | High | Not Started
E3-S2-T2 | Sub-task | E3-S2 | Add accepted_values test for status enum completeness |  | Status Summary Chart | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E3-S3 | Story | E3 | Build mart_ldc_filter_lookups | Distinct values backing each filter/dropdown control. | Queue Filters Panel | Near-Real-Time (≤1hr) | TBD — pending data team |  |  | E2-S1 | Each filter dropdown returns the correct distinct value set. | Story | Medium | Not Started
E3-S3-T1 | Sub-task | E3-S3 | Distinct values for Submitter/Reviewer Group, Seller/Servicer, Sub Status, SLA Status |  | Queue Filters Panel | Near-Real-Time (≤1hr) | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E4 | Epic |  | Redis Cache Sync — Near-Real-Time Tier (≤1hr) | Cache-aside layer between FastAPI and Athena for live queue/status data, refreshed at least hourly. | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  | ldc:* | 1 hour | E3 | Cached endpoints respond <50ms on cache hit; data no more than 1hr stale. | Epic | High | Not Started
E4-S1 | Story | E4 | Design cache key & TTL strategy for near-real-time data |  | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  | ldc:case_queue:<filter_hash>; ldc:status_summary:all | 1 hour |  | Key scheme documented; deterministic for identical filter sets. | Story | High | Not Started
E4-S1-T1 | Sub-task | E4-S1 | Define cache key pattern for case queue (filter-hash based) |  | Case Queue Table | Near-Real-Time (≤1hr) |  | ldc:case_queue:<filter_hash> | 1 hour |  |  | Sub-task | High | Not Started
E4-S1-T2 | Sub-task | E4-S1 | Define cache key pattern for status summary |  | Status Summary Chart | Near-Real-Time (≤1hr) |  | ldc:status_summary:all | 1 hour |  |  | Sub-task | High | Not Started
E4-S1-T3 | Sub-task | E4-S1 | Set TTL = 1hr; define cache-aside fallback to Athena on miss |  | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  |  | 1 hour |  |  | Sub-task | High | Not Started | Fail-open: Redis miss/outage falls through to Athena.
E4-S2 | Story | E4 | Build scheduled sync job (≤1hr cadence) |  | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  |  | 1 hour | E4-S1, E3 | EventBridge-triggered job runs hourly without manual intervention. | Story | High | Not Started
E4-S2-T1 | Sub-task | E4-S2 | EventBridge hourly schedule triggering dbt run + cache-sync |  | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  |  | 1 hour |  |  | Sub-task | High | Not Started
E4-S2-T2 | Sub-task | E4-S2 | Cache-sync script populates Redis from case_queue & status_summary marts |  | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  |  | 1 hour |  |  | Sub-task | High | Not Started
E4-S2-T3 | Sub-task | E4-S2 | Flush/invalidate stale keys before each repopulation |  | Case Queue Table, Status Summary Chart | Near-Real-Time (≤1hr) |  |  | 1 hour |  |  | Sub-task | Medium | Not Started
E4-S3 | Story | E4 | PLACEHOLDER — validate whether ≤1hr is sufficient for the live case queue | Case queue is an active workflow tool; analysts may need to see status changes faster than hourly. | Case Queue Table, Status Summary Chart | ⚠ TBD (<15min?) |  |  | TBD |  | Business confirms acceptable max staleness for queue status fields. | Story | High | Not Started | ⚠ PLACEHOLDER — will clarify
E4-S3-T1 | Sub-task | E4-S3 | NEEDS CLARIFICATION: confirm if Request Status/Sub Status/Queue Age need <15-min refresh | If yes, rework EventBridge cadence, cache TTL, and consider CDC/streaming from source Iceberg tables instead of polling. | Case Queue Table, Status Summary Chart | ⚠ TBD (<15min?) |  |  | TBD |  |  | Sub-task | High | Not Started | ⚠ PLACEHOLDER — will clarify
E5 | Epic |  | Redis Cache Sync — Snapshot Tier (EOD/EOM) | Point-in-time cached aggregates for historical/summary reporting views. | Lender Performance Metrics, Seller Servicer Summary Report (other workbook tabs — scope TBD) | Snapshot (EOD/EOM) |  | ldc:snapshot:* | 24h (EOD) / 1 month (EOM) | E3 | Snapshot keys populate once daily and once monthly without overwriting prior history. | Epic | Medium | Not Started | Scope depends on E5-S1-T1 clarification.
E5-S1 | Story | E5 | Design snapshot cache strategy for EOD/EOM reporting |  | Lender Performance Metrics, Seller Servicer Summary Report | Snapshot (EOD/EOM) |  | ldc:snapshot:eod:<YYYY-MM-DD>; ldc:snapshot:eom:<YYYY-MM> | TBD |  | Scope of snapshot-tier components confirmed; key/retention scheme documented. | Story | Medium | Not Started
E5-S1-T1 | Sub-task | E5-S1 | PLACEHOLDER: confirm which components/reports need EOD/EOM snapshot vs. live queue | e.g., Lender Performance Metrics and Seller Servicer Summary Report tabs in the same workbook may be separate dashboards — confirm scope. | All | ⚠ TBD (<15min?) | [5 empty] | Sub-task | Medium | Not Started | ⚠ PLACEHOLDER — will clarify
E5-S1-T2 | Sub-task | E5-S1 | Define snapshot cache key pattern (date-stamped) |  |  | Snapshot (EOD/EOM) |  | ldc:snapshot:eod:<date> |  |  |  | Sub-task | Low | Not Started
E5-S1-T3 | Sub-task | E5-S1 | Define snapshot retention/TTL for trend views |  |  | Snapshot (EOD/EOM) |  |  | TBD |  |  | Sub-task | Low | Not Started
E5-S2 | Story | E5 | Build EOD/EOM snapshot sync job |  | Lender Performance Metrics, Seller Servicer Summary Report | Snapshot (EOD/EOM) |  |  |  | E5-S1, E3 | Snapshot job runs on EOD and EOM schedule and writes immutable point-in-time keys. | Story | Medium | Not Started
E5-S2-T1 | Sub-task | E5-S2 | EventBridge daily (EOD) + monthly (EOM) schedule triggering dbt run + snapshot sync |  |  | Snapshot (EOD/EOM) | [5 empty] | Sub-task | Medium | Not Started
E5-S2-T2 | Sub-task | E5-S2 | Snapshot sync writes point-in-time aggregates without overwriting prior snapshots |  |  | Snapshot (EOD/EOM) | [5 empty] | Sub-task | Medium | Not Started
E6 | Epic |  | FastAPI Endpoints | Thin read layer over cached/Athena data for the Angular MFE. | All | Near-Real-Time (≤1hr) |  |  |  | E4, E5 | All endpoints documented in Swagger and verified against prototype UI. | Epic | High | Not Started
E6-S1 | Story | E6 | Build GET /api/ldc/case-queue |  | Case Queue Table, Queue Filters Panel | Near-Real-Time (≤1hr) |  | ldc:case_queue:<filter_hash> | 1 hour | E4, E3-S1 | Returns paginated rows matching all 16 queue columns; filters match prototype's 14 filter fields. | Story | High | Not Started
E6-S1-T1 | Sub-task | E6-S1 | Implement filter params matching Queue Filters panel | Request No, Submitter Name/Group, Seller/Servicer Number, Reviewer Group/Name, FM Loan #, Loan Attribute, Sub Status, Submission/Completion Date range, SLA Status. | Queue Filters Panel | Near-Real-Time (≤1hr) | [5 empty] | Sub-task | High | Not Started
E6-S1-T2 | Sub-task | E6-S1 | Implement pagination (default 25 rows) + sort newest-to-oldest |  | Case Queue Table | Near-Real-Time (≤1hr) | [5 empty] | Sub-task | Medium | Not Started
E6-S1-T3 | Sub-task | E6-S1 | Wire cache-aside read from near-real-time Redis tier with Athena fallback |  | Case Queue Table | Near-Real-Time (≤1hr) | [5 empty] | Sub-task | High | Not Started
E6-S2 | Story | E6 | Build GET /api/ldc/status-summary |  | Status Summary Chart | Near-Real-Time (≤1hr) |  | ldc:status_summary:all | 1 hour | E4, E3-S2 | Counts match chart in prototype; supports click-to-filter contract with frontend. | Story | High | Not Started
E6-S2-T1 | Sub-task | E6-S2 | Return per-status counts; support click-to-filter contract with frontend |  | Status Summary Chart | Near-Real-Time (≤1hr) | [5 empty] | Sub-task | High | Not Started
E6-S3 | Story | E6 | Build filter/lookup endpoints |  | Queue Filters Panel | Near-Real-Time (≤1hr) |  | ldc:filters:* | 6 hours | E3-S3 | Each dropdown/typeahead returns correct distinct values. | Story | Medium | Not Started
E6-S3-T1 | Sub-task | E6-S3 | Typeahead/dropdown endpoints for each filter field |  | Queue Filters Panel | Near-Real-Time (≤1hr) | [5 empty] | Sub-task | Medium | Not Started
E6-S4 | Story | E6 | Build export endpoint |  | Case Queue Table (Export) | Near-Real-Time (≤1hr) |  |  |  | E6-S1 | Export output matches columns shown in queue exactly, per prototype note. | Story | Low | Not Started
E6-S4-T1 | Sub-task | E6-S4 | CSV export matching same columns as queue view |  | Case Queue Table (Export) | Near-Real-Time (≤1hr) | [5 empty] | Sub-task | Low | Not Started
E7 | Epic |  | Testing & Data Quality | dbt tests, API tests, and cross-account validation. | All | Infra / N-A |  |  |  | E2, E3, E6 | All test suites green before handoff. | Epic | Medium | Not Started
E7-S1 | Story | E7 | dbt test coverage |  | All | Infra / N-A |  |  |  | E2, E3 | not_null/unique/accepted_values tests pass on all staging + mart models. | Story | Medium | Not Started
E7-S1-T1 | Sub-task | E7-S1 | not_null/unique/accepted_values tests across staging + marts |  | All | Infra / N-A | [5 empty] | Sub-task | Medium | Not Started
E7-S2 | Story | E7 | FastAPI endpoint test suite |  | All | Infra / N-A |  |  |  | E6 | Pytest suite covers filters, pagination, and cache hit/miss paths. | Story | Medium | Not Started
E7-S2-T1 | Sub-task | E7-S2 | Pytest coverage for filters, pagination, cache hit/miss paths |  | All | Infra / N-A | [5 empty] | Sub-task | Medium | Not Started
E7-S3 | Story | E7 | Cross-account data validation |  | All | Infra / N-A | TBD — pending data team |  |  | E1, E3 | Mart row counts and sample values reconcile against source Iceberg baseline. | Story | Medium | Not Started
E7-S3-T1 | Sub-task | E7-S3 | Validate mart output against source Iceberg baseline counts/samples |  | All | Infra / N-A | TBD — pending data team |  |  |  |  | Sub-task | Medium | Not Started
E8 | Epic |  | Documentation & Handoff | API contract docs and open-question tracking for frontend handoff. | All | Infra / N-A |  |  |  | E6 | Frontend team has everything needed to integrate without backend follow-up. | Epic | Low | Not Started
E8-S1 | Story | E8 | API contract documentation |  | All | Infra / N-A |  |  |  | E6 | Endpoint paths, params, and response shapes documented and shared with frontend team. | Story | Low | Not Started
E8-S1-T1 | Sub-task | E8-S1 | Document endpoint paths, params, response shapes for frontend team |  | All | Infra / N-A | [5 empty] | Sub-task | Low | Not Started
E8-S2 | Story | E8 | Maintain open questions log |  | All | Infra / N-A |  |  |  |  | Open Questions tab kept current as clarifications resolve. | Story | Low | Not Started
E8-S2-T1 | Sub-task | E8-S2 | Keep Open Questions tab updated as clarifications are resolved |  | All | Infra / N-A | [5 empty] | Sub-task | Low | Not Started

## Attribute Refresh Mapping
LDC Dashboard — Attribute to Refresh Tier Mapping
Source: Q1 2027 LDC Reporting Data Attributes sheet. Source column / Iceberg table TBD pending data team confirmation.
# | Attribute | Dashboard Component(s) | Refresh Tier | Source Field / Iceberg Column (placeholder) | Notes / Assumptions
1 | Request Status | Status Summary Chart, Case Queue Table | Near-Real-Time (≤1hr) | TBD — pending data team | Drives the 6 status-button counts.
2 | Request No. | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team | Primary key for the request.
3 | Submitter Name | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team
4 | Submitter Group | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team | Enum: External Submitter, LDC, MSOPE, CURE, DVC, IR.
5 | Seller Number | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team
6 | Seller Name | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team
7 | Servicer Number | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team
8 | Servicer Name | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team
9 | Reviewer Group | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team | Enum: Auto-Decision, LDC, Sec Policy.
10 | Reviewer Name | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team
11 | FM Loan # | Queue Filters (loan-level drill-in) | Near-Real-Time (≤1hr) | TBD — pending data team
12 | Loan Attribute | Queue Filters (loan-level drill-in) | Near-Real-Time (≤1hr) | TBD — pending data team
13 | Sub Status | Case Queue Table, Queue Filters | Near-Real-Time (≤1hr) | TBD — pending data team | Enum: Draft, Pending Loan Approval, Pending Securitization Approval, Pending Reclass, Request Completed, Partially Processed, Canceled, …
14 | Submission Date | Case Queue Table, Queue Filters (date range) | Near-Real-Time (≤1hr) | TBD — pending data team
15 | Completion Date | Case Queue Table, Queue Filters (date range) | Near-Real-Time (≤1hr) | TBD — pending data team
16 | SLA Status | Case Queue Table, Queue Filters | ⚠ TBD (<15min?) | TBD — pending data team | Calculated field — SLA threshold definition needed (Within SLA / At Risk / Breached).
17 | Queue Age | Case Queue Table | ⚠ TBD (<15min?) | TBD — pending data team | Elapsed-time field — candidate for <15min refresh since it changes continuously while a request is open.
18 | Loan Count | Case Queue Table | Near-Real-Time (≤1hr) | TBD — pending data team | Rollup from loan-level attribute records.
19 | Attribute Count | Case Queue Table | Near-Real-Time (≤1hr) | TBD — pending data team | Rollup from loan-level attribute records.
20 | Cycle Time | Case Queue Table | Snapshot (EOD/EOM) | TBD — pending data team | Only meaningful once Completion Date is set — candidate for snapshot/EOD-computed reporting metric rather than live.

## Open Questions
Open Questions & Placeholders
# | Question / Placeholder | Area | Priority | Status
1 | Does the live Case Queue (Request Status, Sub Status, Queue Age) need <15-min refresh instead of ≤1hr, given analysts actively work this queue? | Refresh Cadence | High | Open
2 | What are the exact Iceberg database/table names in the source data team's AWS account for LDC case request data? | Source Integration | High | Open
3 | What is the process/owner for the cross-account IAM trust policy and Lake Formation grants? | Source Integration | High | Open
4 | What are the SLA Status thresholds (Within SLA / At Risk / Breached)? | Business Logic | High | Open
5 | Is Queue Age / Cycle Time calculated in calendar days or business days, and in which time zone? | Business Logic | High | Open
6 | Do the other workbook tabs (Detailed Reporting Export, Lender Performance Metrics, Seller Servicer Summary Report) belong to this same dashboard build, or are they separate deliverables? | Scope | Medium | Open
7 | Should cache invalidation be schedule-only, or also event-triggered on dbt test failure / data-quality alert? | Cache Strategy | Medium | Open
8 | What is the maximum expected row volume for export, to validate Redis value size limits for cached payloads? | Cache Strategy | Low | Open

## Refresh Tier Definitions
Refresh Tier Definitions & Sync Pattern Reference
Tier | Definition | Sync Pattern (proposed) | Notes
Snapshot (EOD/EOM) | Refreshed once per day (end of day) or once per month (end of month). Used for historical / point-in-time reporting views. | EventBridge daily/monthly schedule → dbt run → snapshot cache-sync writes date-stamped Redis keys. | Likely fits Lender Performance Metrics / Seller Servicer Summary Report style views — scope TBD.
Near-Real-Time (≤1hr) | Refreshed at least hourly via scheduled dbt run + cache sync. Acceptable for dashboards where up-to-1hr staleness is tolerable. | EventBridge hourly schedule → dbt run → cache-sync repopulates Redis; cache-aside fallback to Athena on miss. | Current default assumption for the Case Queue and Status Summary chart.
⚠ TBD (<15min?) | Not yet in scope. Flagged per-attribute/component where live use (active case management) suggests sub-hourly latency may be required. | Design pending clarification — may require a more frequent EventBridge schedule, change-data-capture/streaming from source Iceberg tables, or a direct Athena passthrough without caching for the affected fields only. | Primary candidates: Request Status, Sub Status, Queue Age (see Open Questions tab).