## Reporting Service Project Plan
Reporting Dashboard MFE — Project Plan
Fannie Mae — Loan Servicing Platform ¦ MSR17051-HT7 ¦ Covers: Option 1 (Angular + Python Custom Build) & Option 2 (Tableau) ¦ DRAFT
Type | Task Name | Option | Assigned To | ETA | Status | Notes
Asset Setup | BAR Registration (Reporting Dashboard Backend) | Both |  | 1 Week | Not Started | Obtain MSR number for backend. Critical path — blocks SFST deployment.
Asset Setup | APP Short Name Registration | Both |  | 2 Days | Not Started | Register short name in Fannie Mae asset registry.
Asset Setup | AWS Onboarding (SFST Account) | Both |  | 1 Week | Not Started | Onboard into SFST AWS account. Required for all cloud resource provisioning.
Asset Setup | UDP Onboarding | Both |  | 3 Days | Not Started | Universal Data Platform onboarding for data access governance.
Asset Setup | DataFlow ID Registration | Both |  | 1–2 Weeks | Not Started | Register data flow between SDL/LSDL and the reporting service.
Asset Setup | FMSSO Onboarding | Both |  | 3 Days | Not Started | Fannie Mae SSO onboarding — required for Ping Identity integration.
Asset Setup | AI Dome Key Onboarding | Both |  | TBD | Not Started | Required if NLQ/Agentic AI (Bedrock) features are in scope.
Asset Setup | ICR Producer/Consumer Contracts | Both |  | 1 Week | Not Started | Define data producer/consumer contracts for Aurora and SDL data sources.
AD Group Creation | Create AD Group — Reporting Dashboard Developers | Both |  | 2 Days | Not Started | AD group for dev team access to AWS resources, ECR, S3, Secrets Manager.
AD Group Creation | Create AD Group — Reporting Dashboard Viewers (Internal) | Both |  | 2 Days | Not Started | Internal Fannie Mae users — read-only access to reporting views.
AD Group Creation | Create AD Group — Reporting Dashboard Viewers (Servicer) | Both |  | 2 Days | Not Started | External servicer users — scoped access via Ping Identity + Apigee.
AD Group Creation | Create AD Group — Tableau / BI Admins | Tableau |  | 2 Days | Not Started | Option 2 only: AD group for Tableau Server administrators on EC2.
CI/CD Setup | GitLab Runners / Workspace Setup | Both |  | 1 Week | Not Started | Configure GitLab runners for Angular build and Docker image build pipelines.
CI/CD Setup | Terraform Workspace | Both |  | 1 Week | Not Started | Terraform workspace for IaC — S3 bucket, CloudFront, ECS, ALB provisioning.
CI/CD Setup | Provision Infra (ECS) — CI/CD Pipelines | Both |  | 1 Week | Not Started | ECS Fargate task definition, ECR repo, ALB, target groups via pipeline.
CI/CD Setup | Integrate with Secrets Manager | Both |  | 1 Week | Not Started | Wire AWS Secrets Manager into ECS task for DB credentials and API keys.
CI/CD Setup | Environment-Specific Configs (dev/staging/prod) | Both |  | 2–3 Days | Not Started | Environment variable sets per deployment stage. Angular environment.ts files.
CI/CD Setup | Code Deploy — S3 + CloudFront Invalidation | Both |  | TBD | Not Started | Angular build → S3 → CloudFront cache invalidation on every deploy.
SSO / Auth Setup | Register Portal as Ping Identity SAML SP | Both |  | 3 Days | Not Started | Register the Loan Servicing Portal as SAML Service Provider in PingFederate.
SSO / Auth Setup | Obtain Ping Identity Client Credentials | Both |  | 3 Days | Not Started | Client ID/secret for OAuth2/SAML flows. Store in Secrets Manager.
SSO / Auth Setup | Configure Apigee API Gateway Routes | Both |  | 1 Week | Not Started | Register Reporting Service backend routes in Apigee. JWT validation policy.
SSO / Auth Setup | Validate SSO Cross-App Session (Portal → Target App) | Both |  | 2 Days | Not Started | Verify no re-auth prompt when navigating from portal to reporting views.
Data Setup | Aurora PostgreSQL Schema Design | Both |  | 1 Week | Not Started | Define canonical schema: delinquency, escrow, cash position, reclassification.
Data Setup | Data Migration: CSV → Aurora | Both |  | 1 Week | Not Started | Migrate PoC CSV data. Run parallel validation against CSV baseline.
Data Setup | SDL / LSDL Data Lake Read Pattern | Both |  | 1–2 Weeks | Not Started | Coordinate with SDL team. Athena query patterns for large historical datasets.
Data Setup | Amazon SQS + EventBridge — Async Report Jobs | Both |  | 1 Week | Not Started | Queue design for large async report generation. EventBridge for scheduled jobs.
Frontend Infra | S3 Bucket — Angular MFE Static Hosting | Option 1 |  | 2 Days | Not Started | Create versioned S3 bucket in SFST account for Angular build artifacts.
Frontend Infra | CloudFront Distribution — MFE | Option 1 |  | 2 Days | Not Started | CloudFront CDN in front of S3. Configure OAC, cache behaviours, HTTPS.
Frontend Infra | CloudFront WAF Rules — External Servicer Path | Option 1 |  | 3 Days | Not Started | WAF ACL for servicer-facing CloudFront. Block non-Fannie-Mae origins.
Frontend Infra | Angular Build Pipeline — Nexus Registry Config | Option 1 |  | 2 Days | Not Started | Configure npm to proxy through Fannie Mae Nexus. Validate all package resolves.
Frontend Infra | Module Federation — Register MFE in Portal Shell | Option 1 |  | 3 Days | Not Started | Register Reporting Dashboard remote in host shell webpack config. Route setup.
Frontend Infra | Plotly.js Local Asset Bundle Verification | Option 1 |  | 1 Day | Not Started | Confirm plotly.min.js in assets/ loads correctly post-CloudFront deploy.
Backend Infra | ECR Repository — Reporting Service Docker Image | Option 1 |  | 1 Day | Not Started | Create ECR repo in SFST account. Set lifecycle policy for image retention.
Backend Infra | ECS Fargate Task Definition — FastAPI Service | Option 1 |  | 2 Days | Not Started | Task def: Fannie Mae base image, CPU/memory, env vars, Secrets Manager ref.
Backend Infra | Application Load Balancer + Target Group | Option 1 |  | 2 Days | Not Started | ALB in private subnet. HTTPS listener, health check path /health.
Backend Infra | ECS Service — Auto Scaling Policy | Option 1 |  | 2 Days | Not Started | Target tracking on CPU. Min 2, max 10 tasks for 2,000+ user load.
Backend Infra | Security Groups — ECS ↔ ALB ↔ Aurora | Option 1 |  | 1 Day | Not Started | Least-privilege SG rules: ALB → ECS on 8000, ECS → Aurora on 5432.
Backend Infra | FastAPI JWT Middleware — Ping Identity JWKS | Option 1 |  | 2 Days | Not Started | python-jose JWKS validation. Fetch public keys from Ping Identity endpoint.
Backend Infra | CloudWatch Log Groups + X-Ray Tracing | Option 1 |  | 1 Day | Not Started | ECS task log group, retention 30 days. X-Ray segment for API latency tracking.
Tableau Site Creation | Create Tableau Server Site — Reporting Dashboard | Option 2 |  | 2 Days | Not Started | Create dedicated Tableau Server site scoped to reporting dashboard content.
Tableau Site Creation | Configure Site Roles — Creator / Explorer / Viewer | Option 2 |  | 1 Day | Not Started | Map AD groups to site roles. Internal = Explorer. Servicer = Viewer.
Tableau Site Creation | Publish Data Sources — Aurora PostgreSQL | Option 2 |  | 2 Days | Not Started | Install Tableau PostgreSQL JDBC driver on EC2. Publish live data source.
Tableau Site Creation | Publish Data Sources — Amazon Athena (SDL) | Option 2 |  | 2 Days | Not Started | Install Tableau Athena ODBC/JDBC connector on EC2. Publish SDL data source.
Tableau Site Creation | Configure Extract Schedule (TDE/.hyper) | Option 2 |  | 1 Day | Not Started | Set incremental extract refresh schedule for Aurora and Athena data sources.
Tableau Site Creation | Enable Ask Data NLQ — Synonym Configuration | Option 2 |  | 2 Days | Not Started | Configure field synonyms: delinquency, escrow, cash position, servicer ID.
Tableau Site Creation | Publish Workbooks — 6 Dashboard Components | Option 2 |  | 2 Days | Not Started | Publish bar, line, pie, tabular, summary tile, global filter workbooks.
Tableau Infra | Tableau Server EC2 — SSL Certificate Install | Option 2 |  | 1 Day | Not Started | SHA-2 SSL cert required for SAML. Install on Tableau Server EC2 instance.
Tableau Infra | Register Tableau Server as Ping Identity SAML SP | Option 2 |  | 2 Days | Not Started | Separate Ping SAML SP connection for Tableau. Entity ID must match tsm config.
Tableau Infra | Set wgserver.saml.forceauthn = false | Option 2 |  | 1 Day | Not Started | Prevents re-auth prompt when navigating from portal. Verify via tsm get.
Tableau Infra | Configure CSP / X-Frame-Options for MFE Embedding | Option 2 |  | 2 Days | Not Started | Relax X-Frame-Options for portal domain. Portal CSP frame-src exception needed.
Tableau Infra | Tableau Embedding API v3 — Angular Integration | Option 2 |  | 2 Days | Not Started | Integrate tableau-viz Web Component into Angular MFE. Handle JWT handoff.
Tableau Infra | Performance Test — 2,000+ Concurrent Viewer Sessions | Option 2 |  | 3 Days | Not Started | Load test Tableau Server EC2 at scale. Tune JVM heap, worker process count.
Monitoring | CloudWatch Dashboard — ECS + ALB Metrics | Both |  | 1 Day | Not Started | CPU, memory, request count, 4xx/5xx error rate, ALB latency metrics.
Monitoring | CloudWatch Alarms — Error Rate + Latency Thresholds | Both |  | 1 Day | Not Started | Alert on p99 latency > 2s, 5xx rate > 1%. SNS → team email.
UAT | Internal User UAT — CDX Ingress Path | Both |  | 3 Days | Not Started | Validate report views for internal Fannie Mae users via CDX routing.
UAT | External Servicer UAT — CloudFront / DMZ Path | Both |  | 3 Days | Not Started | Validate report views for servicer users via CloudFront + DMZ + Ping SSO.
UAT | Cross-Browser Testing — Chrome, Edge, Firefox | Both |  | 2 Days | Not Started | Verify SSO session, chart rendering, and report filters across all browsers.
Colour key: BLUE = Shared / both options GREEN = Option 1 (Angular + Python custom build) only AMBER = Option 2 (Tableau) only ¦ Status: Not Started / In Progress / Blocked / Complete